## Risks
Description | Evaluation | Likelihood | Impact level | Responsibility | Response | Control Measure | ID
Github crashes | I lose all my version history and work | Low | High | GitHub | Restart Project | Keep a secondary backup of most recent working project build | 1
My Glasses Break | Harder to focus on code | Low | Low | Me | Get a new pair | Maintain safe usage and storage | 2
API Breaks | Front and Backend failures | Low | High | Me | Return to working version | Maintain MVP at all times when tinkering | 3
Real life problem requires attention | Stop coding to sort issue | High | Medium | Me | Sort issue and return to coding when able | Sort life issue after work and make sure no commitments are set during work times | 4
Project MVP requirements change | Previous work is useless | Low | Medium | Customer | Salvage existing code that can be used and replan | Keep updated with the Customer product scope page | 5
Keyboard and Mouse faults | Can't use desktop to code | Medium | Medium | Manufacturer | Go buy new equipment or borrow laptop | Maintain safe peripheral usage | 6
Internet goes down | Can't connect to JIRA or gitHub | Medium | Low | Virgin Media | Use Hotspot from Phone | Ethernet connect into router to avoid wifi drops | 7
Testing Fails and results in under standard coverage | API is not valid | Low | High | Me | Reverse engineer API from testing failures | Continuous testing to excessive issues at the end | 8
Low Productivity | Incomplete or below standard project | Low | High | Me | centre and re-focus | Every morning have a reasonable idea of what can be achieved | 9
Main PC breaks | Can't code on my prefered device | Low | Low | Me | Continue on second desktop or laptop | Maintain safe usage and monitor temperatures at application launches | 10

## Matrix
LIKELIHOOD | IMPACT LEVEL
| LOW | MEDIUM | HIGH
LOW | 2,10 | 5 | 1,3,8,9
MEDIUM | 7 | 6
HIGH |  | 4